## Alice Morgan
Name: Alice Morgan |  | Project Group (Name/Number): Group 6
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
11 | 2023-07-27 | Meeting: initial idea brainstorming with group | 1 hour | All | Yes
12 | 2023-08-01 | Met with team to do SWOT analysis & brainstorm ideas | 30 minutes | All | Yes
13 | 2023-08-07 | Meeting: spoke with some of the group outside of the session to discuss our ideas. Working idea is: space-themed game (to tie in with Thales' work in aerospace) using a Thales Stratobus-type aircraft. The user will navigate around a map completing challenges and answering questions. We will use a space API to e.g. get weather conditions in Earth's atmosphere/on another planet and the player will have to report this back to Earth. SQL will be used to store questions & answers and potentially to log the player's score | 1 hour | Rea, Natalie, Kirsty, Alice, Perrine | Yes
13 | 2023-08-09 | Group meeting: Finalising Week 2 homework (project outline, objective, flow diagram). | 1 hour | All | Yes
13 | 2023-08-10 | Group Stand-up meeting | 30 minutes | All | Yes
14 | 2023-08-14 | Research on connecting MySQL to PyCharm and made a start on making the database for the quiz questions as well as coming up with the quiz questions. | 2 hours | Alice | Made a start!
14 | 2023-08-15 | Continued to work on the DB and Python code for the quiz | 1 hour | Alice | Yes
14 | 2023-08-16 | Stand-up meeting | 30 minutes | Rea, Natalie, Kirsty, Alice, Perrine | Yes | I experienced some tech issues during this call and was only able to listen in!
14 | 2023-08-17 | Completed quiz database and python code for the quiz. Also completed the leaderboard database - all posted on quiz branch. | 2 hours | Alice | Yes | Successfully completed all code, however, I encountered the problem of the SQL db only accessible locally with same user login - had to speak to Derrick about this this evening and we discussed options to make it globally accessible. In the end, Kirsty was able to find a solution through SQLite!
14 | 2023-08-17 | Stand-up meeting | 30 minutes | All | Yes
14 | 2023-08-18 | Unit test for python code and looked through/tested code so far. Wrote comments for the game.py | 2 hours | Alice | Yes
15 | 2023-08-21 | Stand-up meeting | 30 minutes | All | Yes | NB - was unable to complete coding work as planned on Sun/Mon due to Eplieptic seizure and recovery! Also had to stay behind to speak to Luke as have been experiencing a lot of issues with GitHub and PyCharm - issue not resolved until next day.
15 | 2023-08-22 | Made a good start on README doc and research around it | 2 hours | Alice | Yes
15 | 2023-08-22 | Stand-up meeting | 45 minutes | All | Yes
15 | 2023-08-23 | Completed README doc on GitHub | 1-2 hours | Alice | Yes
15 | 2023-08-23 | Stand-up meeting | 45 minutes | All | Yes
15 | 2023-08-24 | Stand-up meeting/group time during session | 1 hour | All | Yes
15 | 2023-08-24 | Project Report and user testing | 2 hours | Alice | Yes
15 | 2023-08-25 | Project Report | 1-2 hours | Alice | Yes
15 | 2023-08-26 | Final edits and checks and sent out new version of report | 2 hours | Alice | Yes
15 | 2023-08-27 | Group meet, final edits and review etc - also discussion about presentation on Friday | 1 hour | Alice, Kirsty, Louise, Natalie, Perrine | Yes
15 | 2023-08-27 | Project Report, README doc and final checks | 1-2 hours | Alice | Yes
15 | 2023-08-27 | Final call to submit project and final checkts etc. |  | Alice, Kirsty, Louise, Natalie, Perrine | Yes

## Kirsty McVean
Name: Kirsty McVean |  | Project Group (Name/Number): Group 6
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
11 | 2023-07-27 | Google Meet added some ideas to the Trello board for discussion, discussed during the session the idea of a submarine using RaspberryPi Ultrasonic sensor to contoll the sub depth, were advised not to use hardware for testing purposes and found out that the other Thales group are choosing an underwater game. Agreed to make a space game! :D | 30 | All | Yes | https://trello.com/invite/b/cKhUegDM/ATTI52f358caa1ef6913609c7b7274e7d71c95FF8C14/thales-gals
11 | 2023-07-28 | Researched some Thales products to base the game on, an atmosphere API that can give wind direction, researched another font end option - PySimpleGUI. Shared in Discord | 60 |  | Yes
12 | 2023-08-01 | Google meet with the group to do SWOT analysis and brainstorm ideas | 60 | All | Yes | https://app.mural.co/t/thalesgals2589/m/thalesgals2589/1690487341455/936abfd38035f589f9eb8db617ecbecf41700ec6?sender=u3b49fb67af5a4b1b7dbd7137
13 | 2023-08-07 | Google meet to finalise plan, had written some code to call the sentinel hub API for satellite images, shared in Discord | 60 | Rea, Natalie, Kirsty, Alice, Perrine | Yes
13 | 2023-08-09 | Google meet to look over homework drafted by others | 60 | All | Yes
|  | Drafted a pygame template including a scene manager with buttons | 120 |  | Yes | https://github.com/CFGSoftware2-23/Group-6-Thales-Gals/tree/test
13 | 2023-08-10 | stand-up meeting | 20 | All | Yes
13 | 2023-08-11 | Made typwriter module, upoaded to test branch | 120 |  | Yes
14 | 2023-08-13 | Pair coding of pygame with Louise, linked asteroid mission returns to pygame succesfully, uploaded to test branch | 60 | Lousie | Yes
14 | 2023-08-14 | stand-up meeting | 20 | Rea, Perrine, Kirsty | Yes
33 |  | Updated typwriter module to adapt to text size, also updated the button module | 60 |  | Yes
14 | 2023-08-15 | stand-up meeting | 20 | Rea, Natalie, Kirsty, Alice, Perrine | Yes
|  | starting blitting Perrine's pngs onto scenes | 60 |  | Yes
14 | 2023-08-16 | stand-up meeting | 30 | Rea, Natalie, Kirsty, Alice, Perrine | Yes
33 |  | Made TextInput module, and other asteroid scene tweaks | 180 |  | Yes
14 | 2023-08-17 | stand-up meeting | 30 | All | Yes
|  | Made cloud analyser module | 60 |  | Yes
14 | 2023-08-18 | Completed asteroid scene with pass and fail messages, button removal on fail. Added audio including background music, button sounds and mute option | 300 |  | Yes
14 | 2023-08-19 | Worked on asteroid mission pygame implementation | 300 |  | Yes
15 | 2023-08-20 | Completed Asteroid mission and resolved merge conflicts on test branch, wrote a little guide to comparing changes in pycharm to share Started Quiz scene | 300 |  | Yes | https://discord.com/channels/1109373429276221460/1129130417958703205/1142511845962432564
15 | 2023-08-21 | stand-up meeting | 30 | All | Yes
|  | worked on quiz pygame scene from quiz/database logic, first question rendered | 480 |  | Yes
15 | 2023-08-22 | stand-up meeting | 45 | All | Yes
|  | Finished debugging the quiz, started looking at integrating ISS mission | 180 |  | Yes
15 | 2023-08-23 | stand-up meeting | 45 | All | Yes
|  | fixed new bug in asteroid mission, integrated the mars mission | 240 |  | Yes
15 | 2023-08-24 | stand-up meeting |  | All | Yes
|  | added loading to mars scene |  |  | Yes
15 | 2023-08-25 | group call, pygame discussion | 30 | Perrine, Kirsty, Louise | Yes
|  | Made end screen | 120 |  | Yes
15 | 2023-08-26 | refactored files and tested unit tests so far | 480 |  | Yes
16 | 2023-08-27 | last two meetings before submission 😁 | 180 | All | Yes
|  | Tiding up code, last few bugs and unit tests | 300 |  | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit?pli=1
Formulas:
Week: = WEEKNUM([Date:])- 19

## Louise Berridge
Name: Louise Berridge |  | Project Group (Name/Number): Group 6
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | Yes | EXAMPLE
11 | 2023-07-27 | In Thales WhatsApp group Suggested educational space game as project idea and include facts about Thales space projects like Jupiter’s Icy moons explorer (JUICE). So my idea is an educational space game which can include facts about thales space missions (e.g. juice - jupiter icy moons explorer something like that anyway). Could be questions about planets etc and if on a section about jupiter could have simple qs about the planet, then add at the end . Did you know Thales have sent a satellite to explore Jupiter’s moons? Searched for and researched space API for space quiz and posted to discord chat: https://nordicapis.com/11-space-apis-because-space-is-neat/ # 7 has solar system info, brief look at documentation Researched potential framework for space game and posted answer to project discord chat | 50 | Thales whatsapp group | N/A | Thales Whatsapp/project discord
11 | 2023-07-27 | Google meet. See minutes. We decided to do something Thales related they are our sponsor. Discussing project ideas. Suggested another idea using google translate api as Thales is an international company we could do something with this to make sure all colleagues understand each other/documents when working with teams in other countries (although they will most definitely have something in place already). | 30 | All | N/A | Discord project group
11 | 2023-07-29 | Researched how to make a quiz in python and pygame. Posted link to YouTube video re pygame to project discord chat ( https://pythonprogramming.altervista.org/a-quiz-made-with-pygame-how-to/) and read associated documentation. Coded basic python quiz game using another YouTube tutorial but my own questions with a view to setting up link to SQL to store questions and answers later. Started to look at designing quiz using pygame. Not completed. (Before we decided on each persons roles. | 120 | Me | N/A
12 | 2023-08-01 | Attended meeting to finalise ideas and attempt homework2 | 60 | All | N/A | Google meets
12 | 2023-08-01 | Started to make sql database for quiz, although this has been allocated to Alice now, so not continued. | 30 | Me | N/A
13 | 2023-08-08 | Research re linking sql to pygame. Found YouTube on how to create leaderboard and quiz using mysql and python, sent links to discord project chat as this has been allocated to Alice. https://youtu.be/2xuDZkQV_c8?list=PLejGx5HlC6TLrPlyfEFCTAJ_GaWCuy0to, https://youtu.be/M63LHdpVhp8?list=PLejGx5HlC6TLrPlyfEFCTAJ_GaWCuy0to | 30 | Me | N/A
13 | 2023-08-09 | Finalised homework suggested some additions. We all agreed to do daily standup | 30 | All | Yes
13 | 2023-08-10 | Daily standup. Me and Kirsty to meet to work on pygame. I noticed a bug in asteroid game - not rounding down when it should due to int(), instead of round() being used. Mentioned to group. | 20 | All |  | In breakout room in last part of class
13 | 2023-08-13 | Meeting with Kirsty in Discord study room to discuss how we want to display our project in pygame and how we can extract what we need from the different mission files into pygame. Started to pair code together to refactor the asteroid challenge mission to pygame. Starting by changing the print statements to return statements and trying to get the greet() method to display in pygame. Decided to go and research ourselves and see what we could find. | 30 | Louise, Kirsty | In progress | Discord study room
13 | 2023-08-13 | We both managed to get the greet() function to display in pygame, roughly around the same time | 30 | Louise, Kirsty | Yes
14 | 2023-08-14 | Chat in discord about project. Re quiz game and sql. | 30 | All | N/A | Chat on and off throughout the day on discord most days about project
14 | 2023-08-14 | Research and coding to try to get asteroid mission to display in pygame. Started with trying to get the code to display to console without using print statement in the methods. Partly successfully as displays the asteroid distances and guess attempt countdown. | 120 | Louise | Partly
14 | 2023-08-15 | Research into how to take user input in pygame. Found class on stack overflow. Trying to implement it with already existing code. | 120 | Louise | Not yet | Discussed on discord and slack
14 | 2023-08-15 | To help learn more about pygame made a basic asteroid dodge game adapted from a tutorial to make it more in line with our project. I added an extra ‘enemy’ and a game over message when there’s a collision. Adapted the theme of the sprites and background to suit our project. | 120 | Louise | Yes
14 | 2023-08-16 | Loaded the background to the asteroid mission scene. | 60 | Louise | Yes
14 | 2023-08-16 | Stand up after class. See meeting minutes. | 30 | All | N/A | See minutes on google doc
14 | 2023-08-16 | Loaded in all the backgrounds to the different scenes for the 5 different missions. Created a menu page with buttons to go to each mission. Coded the navigation between mission pages/menu page/start page | 120 | Louise | Yes
14 | 2023-08-17 | Refactored my asteroid dodge game incl renaming variables, repositioning of enemy, added extra movement to stratobus | 60
14 | 2023-08-17 | Project meeting in class: discussed work on loading mission info into pygame, quiz and sql, pp presentation and documentation. Most people said coding day was Sunday so going to have a meet in the evening to discuss progress | 30 | All | N/a | See minutes on google doc
14 | 2023-08-17 | Sent Kirsty slack message to say what I planned to work on so we don’t overlap: | 10 | Louise, Kirsty | Yes
15 | 2023-08-21 | Stand up. See minutes | 30 | All | Yes | See minutes on google doc
15 | 2023-08-22 | Stand up. Try to implement backgrounds to all scenes etc. and run payload mission in pygame. | 30 | All | Yes | See minutes on google doc
15 | 2023-08-22 | Integrated payload mission to scenes.py and, added background, changed screen size and endgame text position of payload_challenge.py. includes research | 60 | Louise | Yes
15 | 2023-08-22 | Updated scenes, incl background and navigation so that they don’t all loop back to the asteroid input scene, so that they are ready for integration with mission files. Updated some text, font and position of text to fit scenes better | 180 | Louise | Yes
15 | 2023-08-23 | Stand up within lesson. Discussing readme file | 60 | All | Yes | See minutes on google doc
15 | 2023-08-23 | Updated bug fix log with updates I did last night. Fixed accept button and scene for satellite mission play scene. | 60 | Louise | Yes
15 | 2023-08-23 | Integrated ISS mission to main project and pushed to test, added exit button to ISS mission | 60 | Louise | Yes
15 | 2023-08-23 | Tested quiz leader board | 10 | Louise | Yes
15 | 2023-08-23 | Adapted payload game and end game font: so that esc exits game and return allows to play again and pushed to test. | 30 | Louise | Yes
15 | 2023-08-24 | Created new version of asteroid dodge game. User test with my partner went well. | 240 | Louise | Yes
15 | 2023-08-24 | Stand-up with project team. Demoed game, went over things still to do, checked project and discussed bugs. See meeting minutes. | 30 | All | Yes | See minutes on google doc
15 | 2023-08-25 | Tested asteroid dodge again and with my 5yr old son - thumbs up, couldn’t get him off it. Made a pull request to up load changes. Changed pygame window icon to stratobus. Attempted unit testing. Very tricky for me in pygame. None successfully run yet, with a lot of attempts. A lot harder than what we have learnt in class - I can do those. Meeting with Kirsty and Perrine (text only). Trying to get my pull request to work, no luck. Will try tomorrow. Reviewed readme and report. Looking good. Made notes for tomorrow’s stand up re minor updates and changes and for game | 180 | Louise | Yes, except for unit testing
15 | 2023-08-26 | Coms on discord, team problem solving incl ISS mission. Pulled and reviewed new updates from github. Still not able to merge. Added icon update to pygame window (as not done last night through pull request) and adjusted button on welcome screen. Created new feature branch off test to copy files over. Research into unit tests, trying to get them to work. Will have to refactor code a lot. Can’t do at this late stage. | 120 | Louise | Partly
15 | 2023-08-27 | Team work on report | 60 | Alice, Louise, Kirsty, Natalie, Perrine | Mostly | In discord study room
15 | 2023-08-27 | Further work and research on unit test. One now works. Can’t mock a screen blit. Next time, and with more experience I would organise my code differently. Moved the unit test over to test branch and pushed. Me and Natalie notices some button paths don’t work for Mac in latest update. Mentioned in discord. | 60 | Louise | Yes
15 | 2023-08-27 | Final checks and merge to main | 60 | Alice, Louise, Kirsty, Natalie, Perrine | Mostly | In discord study room

## Natalie Martin
60
Name: Natalie Martin |  | Project Group (Name/Number): Group 6
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
11 | 2023-07-27 | Google Meet to brainstorm initial ideas with the group which we captured on Trello. Included an undersea game utilising a raspberry pi sensor and a spacequiz. We agreed we would want the game to reflect Thales' industries. | 30 | All | Yes
11 | 2023-07-27 | Created Trello board and updated with stories | 15 |  | Yes | https://trello.com/b/cKhUegDM/thales-gals
12 | 2023-08-01 | Google Meet to brainstorm ideas, requirements and conduct a SWOT analysis | 60 | All | Yes | https://app.mural.co/t/thalesgals2589/m/thalesgals2589/1690487341455/936abfd38035f589f9eb8db617ecbecf41700ec6?sender=uc4735d0c0a98c349e52d3478
13 | 2023-08-07 | Google Meet to agree on final idea, timelines and delegate stories | 60 | Alice, Kirsty, Perrine, Natalie, Rea | Yes
13 | 2023-08-08 | Researched ideas for payload challenge | 60 |  | Yes
13 | 2023-08-09 | Created GitHub repo & test branch | 10 |  | Yes
13 | 2023-08-09 | Catch up to run through final submission for homework 2 | 60 | All | Yes
13 | 2023-08-10 | Researched ideas for payload challenge - specifically implementation of a tetris-style game | 60 |  | Yes
13 | 2023-08-11 | Created Tetromino class, attributes and methods | 120 |  | Yes
13 | 2023-08-12 | Created GamePlay class and pygame.init() | 180 |  | Yes
13 | 2023-08-13 | Added handlers for event.key | 120 |  | Yes
14 | 2023-08-14 | Bug testing for payload_challenge | 60 |  | Yes
14 | 2023-08-15 | Daily stand-up | 30 | Alice, Kirsty, Perrine, Natalie, Rea | Yes
14 | 2023-08-16 | Daily stand-up | 30 | Alice, Kirsty, Louise, Perrine, Natalie, Rea | Yes
14 | 2023-08-16 | Fixed payload_challenge bug which prevented display | 90 |  | Yes
14 | 2023-08-17 | Daily stand-up | 30 | All | Yes
14 | 2023-08-18 | Updated styles to match rest of game | 30 |  | Yes
14 | 2023-08-19 | Refactored payload_challenge code | 60 |  | Yes
14 | 2023-08-20 | Bug fixes for payload_challenge - game started at the game over screen | 60 |  | Yes
15 | 2023-08-21 | Daily stand-up | 30 | All | Yes
15 | 2023-08-21 | Merged payload_challenge into test | 30 |  | Yes
15 | 2023-08-22 | Daily stand-up | 45 | All | Yes
15 | 2023-08-23 | Daily stand-up | 120 | All | Yes
15 | 2023-08-23 | Started unit tests for payload_challenge | 120 |  | No
15 | 2023-08-24 | Work on unit tests for payload challenge | 60 |  | No
15 | 2023-08-25 | Work on unit tests for payload challenge | 60 |  | No
15 | 2023-08-26 | Created requirements.txt Continued work on unit tests for payload challenge Bug testing for entire game | 240 | All | Yes
15 | 2023-08-27 | Meeting to run through materials and final check list before submission | 120 | Alice, Kirsty, Louise, Perrine, Natalie | Yes
15 | 2023-08-27 | Added docstrings and comments for payload challenge Proof read and edited report | 180 |  | Yes
15 | 2023-08-27 | Finish unit tests for payload challenge | 120 |  | Yes
15 | 2023-08-27 | Meeting to run through any final bugs and submit project | 60 | Alice, Kirsty, Louise, Perrine, Natalie | Yes

## Perrine Hemmings
Name: Perrine Hemmings |  | Project Group (Name/Number): Group 6
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
11 | 2023-07-27 | Researched potential APIs for project | 45 mins | Perrine | Yes | https://rapidapi.com/collection/list-of-free-apis
11 | 2023-07-27 | Group Project Planning Meeting | 1 hr | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
11 | 2023-07-28 | Created Mural board for project collaboration | 1 hr | Perrine | Yes | https://app.mural.co/t/thalesgals2589/m/thalesgals2589/1690487341455/936abfd38035f589f9eb8db617ecbecf41700ec6?sender=u85e99cdc3ba08663d7950127
11 | 2023-07-28 | Researched NASA Space Apis | 1 hr | Perrine | Yes | https://api.nasa.gov/
11 | 2023-07-29 | Illness 31st-3rd | - | Perrine | Yes
12 | 2023-08-06 | Created game process flow on Mural | 2 hrs | Perrine | Yes | https://app.mural.co/t/thalesgals2589/m/thalesgals2589/1690487341455/936abfd38035f589f9eb8db617ecbecf41700ec6?sender=u85e99cdc3ba08663d7950127
13 | 2023-08-07 | Group Meeting to finalise Pygame processess and features | 1 hr | Rea, Natalie, Kirsty, Alice, Perrine | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
13 | 2023-08-07 | Took minutess for group meeting | 20 mins | Perrine | Yes
13 | 2023-08-08 | Researched potential background image ideas | 1 hr | Perrine | Yes
13 | 2023-08-09 | Group Meeting to finalise Homework 2 | 1 hr | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
13 | 2023-08-10 | Created Architecture Diagram for HW2 | 2 hrs | Perrine | Yes | https://docs.google.com/document/d/1bd4rWwSzVlHsb1QDs-mF9K5vJMd54L_ViBFmXK59MeE/edit#heading=h.de0v62sewjj2
13 | 2023-08-10 | Group Standup to see what areas group members are working on/ any issues etc | 30 min | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
13 | 2023-08-11 | Created Initial concept design ideas | 1.5 hrs | Perrine | Yes
13 | 2023-08-12 | Started game design assests | 2 hrs | Perrine | Yes
13 | 2023-08-13 | Worked on Mars Api Code to return images from Mars Rover | 7 hrs | Perrine | Yes
13 | 2023-08-14 | Designed game png images (background scenes/ mission boxes etc) | 2 hrs | Perrine | Yes
14 | 2023-08-14 | Finalised game png images |  | Perrine | Yes
14 | 2023-08-14 | Researched/ sourced potential game music | 30 mins | Perrine | Yes
14 | 2023-08-14 | Edited/ Updated Code for game colours | 20 mins | Perrine | Yes
14 | 2023-08-14 | Group Standup to discuss current progress / areas to work on | 20 min | Rea, Perrine, Kirsty | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
14 | 2023-08-15 | Researched potential game music | 30 mins | Perrine | Yes
14 | 2023-08-15 | Group Standup to discuss current progress / areas to work on | 20 min | Rea, Natalie, Kirsty, Alice, Perrine | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
14 | 2023-08-15 | Pushed game images to github | 20 mins | Perrine | Yes
14 | 2023-08-15 | Refactored Mars API Code to return smaller image in Pygame | 6 hrs | Perrine | Yes
14 | 2023-08-16 | Group Standup to discuss current progress / areas to work on | 30 min | Rea, Natalie, Kirsty, Alice, Perrine | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
14 | 2023-08-16 | Refactored Mars Api Code into Classes | 7 hrs | Perrine | Yes
14 | 2023-08-17 | Group Standup to discuss current progress / areas to work on | 30 min | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
14 | 2023-08-17 | Pushed trivia background and Stratobus pngs to github | 30 mins | Perrine | Yes
14 | 2023-08-18 | Refactored Mars code into classes and pushed to github | 3 hrs | Perrine | Yes
14 | 2023-08-18 | Started on writing code for ISS API Misision | 4 hrs | Perrine | Yes
14 | 2023-08-19 | Continued working on writing ISS API Code | 5 hrs | Perrine | Yes
14 | 2023-08-20 | Redesigned mission screen background and pushed to github | 15 mins | Perrine | Yes
14 | 2023-08-20 | Redesigned and resized png trivia box images and pushed to github | 1.5 hrs | Perrine | Yes
15 | 2023-08-21 | Group Standup to discuss current progress / areas to work on | 30 min | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
15 | 2023-08-21 | Created Group activity log document | 30 mins | Perrine | Yes | https://docs.google.com/spreadsheets/d/1J-myHuuSnNEbxTjSu0C26gK4jsQvPm5uqTSwd7fCUkE/edit#gid=1405708178
15 | 2023-08-21 | Researched and sourced alternative fonts for game text | 30 mins | Perrine | Yes | https://www.dafont.com/theme.php?cat=303
15 | 2023-08-22 | Added new font file to github | 15 mins | Perrine | Yes
15 | 2023-08-22 | Conducted play through/ play test of game | 30 mins | Perrine | Yes
15 | 2023-08-22 | Created bug report on github to track current/ongoing bugs in game | 1 hr | Perrine | Yes
15 | 2023-08-22 | Wrote pre-stand-up itinery of remaining project to-dos | 20 mins | Perrine | Yes
15 | 2023-08-22 | Group Standup to discuss current progress / areas to work on | 45 mins | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
15 | 2023-08-23 | Refactored Mars Mission unit tests, pushed to github | 3 hrs | Perrine | Yes
15 | 2023-08-23 | Refactored Iss Mission unit tests, pushed to github | 3 hrs | Perrine | Yes
15 | 2023-08-23 | Conducted another play through, added bugs found to bug report on github | 20 mins | Perrine | Yes
15 | 2023-08-23 | Group Standup to discuss current progress / areas to work on | 45 mins | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
15 | 2023-08-24 | Refactored new iss mission with new features to power up the space station. pushed to new branch on github | 6 hrs | Perrine | Yes
15 | 2023-08-24 | Started on payload background redesign | 1 hr | Perrine | Yes
15 | 2023-08-24 | Group Standup call | 1.5 hrs | All | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
15 | 2023-08-25 | Designed new payload mission background | 4 hrs | Perrine | Yes
15 | 2023-08-25 | Playthough and added bugs to report | 20 mins | Perrine | Yes
15 | 2023-08-25 | Created Flow Diagram for Project report | 3 hrs | Perrine | Yes
15 | 2023-08-25 | Group Standup call | 30 mins | Perrine, Kirsty, Louise | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
15 | 2023-08-26 | Playthrough and added bugs to report | 30 mins | Perrine | Yes
15 | 2023-08-26 | Refactored Mars mission file to add comments and removed unnedded comments | 1 hr | Perrine | Yes
15 | 2023-08-26 | Refactored ISS Mission and design | 5 hrs | Perrine | Yes
15 | 2023-08-27 | Refactored ISS Mission and design | 4 hr | Perrine | Yes
15 | 2023-08-27 | Group Standup call | 1hr 15min | Perrine, Kirsty, Louise, Alice, Nat | Yes | https://docs.google.com/document/d/1X_6jG4SEUvuh9qnsdbjLzPWe_d1tJoqGbrvcnGSW3GA/edit
15 | 2023-08-27 | Refactored ISS Mission and design, pushed to github | 3 hrs | Perrine | Yes
15 | 2023-08-27 | Refactored Iss Mission unit tests | 3 hrs | Perrine | Yes
15 | 2023-08-27 | Final Group Standup call and submission! :-) | 1 hr | Perrine, Kirsty, Louise, Alice, Nat | Yes | https://github.com/CFGSoftware2-23/Group-6-Thales-Gals/tree/main

## Rea Bartlett Tandon
Name: Rea Bartlett Tandon |  | Project Group (Name/Number): Group 6
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
11 | 2023-07-27 | Meeting: initial idea brainstorming with group | 1h | all | Yes
12 | 2023-08-01 | Met with team to do SWOT analysis & brainstorm ideas | 30m | all | Yes
12 | 2023-08-01 | Individual: researching APIs to use in the game & making notes in shared doc, suggesting potential tasks for the player based on each API. Found lots of APIs on NASA Open API site | 1h | Rea | Yes
12 | 2023-08-07 | Meeting: spoke with some of the group outside of the session to discuss our ideas. Working idea is: space-themed game (to tie in with Thales' work in aerospace) using a Thales Stratobus-type aircraft. The user will navigate around a map completing challenges and answering questions. We will use a space API to e.g. get weather conditions in Earth's atmosphere/on another planet and the player will have to report this back to Earth. SQL will be used to store questions & answers and potentially to log the player's score | 1h | Rea, Natalie, Kirsty, Alice, Perrine | Yes
13 | 2023-08-08 | Individual: rough mockup of how asteroid challenge could be coded | 2h | Rea | Yes
13 | 2023-08-09 | Individual: revising project introduction & objective for week 2 homework | 30m | Rea | Yes
13 | 2023-08-09 | Meeting: finalising week 2 homework (project outline, objective, flow diagram) | 40m | all | Yes
13 | 2023-08-10 | Individual: refactoring code for asteroid challenge: splitting into small functions, creating OOP-based framework for the rest of the challenges to be added to, refactoring asteroid challenge to OOP, drafting some unit tests | 2h | Rea | Yes
13 | 2023-08-11 | Individual: more code refactoring for asteroids challenge, some GitHub admin | 2h | Rea | Yes
14 | 2023-08-14 | Group: daily standup | 30m | Rea, Perrine, Kirsty | Yes
14 | 2023-08-15 | Individual: refactoring code for asteroid challenge, writing Sentinel/satellite challenge code | 9h | Rea | Yes
14 | 2023-08-15 | Group: daily standup | 30m | Rea, Natalie, Kirsty, Alice, Perrine | Yes
14 | 2023-08-16 | Individual: refactoring of sentinel challenge | 3h | Rea | Yes
14 | 2023-08-16 | Group: daily standup | 30m | Rea, Natalie, Kirsty, Alice, Perrine | Yes
14 | 2023-08-17 | Individual: first draft of group project report, making a start on presentation slides | 6h | Rea | Yes
14 | 2023-08-17 | Group: daily standup | 1h | all | Yes
15 | 2023-08-20 | Inividual: unit tests | 3h | Rea | Yes
15 | 2023-08-21 | Individual: GitHub admin, refactoring & unit tests for asteroids & satellite missions, adding docstrings to all functions, commenting code | 7h | Rea | Yes
15 | 2023-08-21 | Group: daily stand-up | 30m | all | Yes
15 | 2023-08-22 | Individual: more code refactoring, unit tests | 3.5h | Rea | Yes
15 | 2023-08-22 | Group: daily stand-up | 30m | all | Yes
15 | 2023-08-23 | Indidivual: implementing satellite mission into PyGame | 5h | Rea | Yes
15 | 2023-08-23 | Group: daily stand-up | 30m | all | Yes
15 | 2023-08-24 | Indidivual: implementing satellite mission into PyGame | 5h | Rea | Yes
15 | 2023-08-23 | Group: daily stand-up | 5h | all | Yes